## Tracker
Synapse → Databricks bridge v9.5.8: implementation tracker
Fill in the yellow columns (Owner, Status, dates, Notes). Readiness updates itself from the dependencies' status. See the Legend tab.
ID | Group | Task | Done when | Package reference | Dep 1 | Dep 2 | Dep 3 | Dep 4 | Owner | Status | Start date | Target date | Readiness | Notes / risks
1 | A. Platform setup | Identities and secrets | Principals created: orchestrator, CETAS login, Synapse managed identity, four Job Run-as principals, deployment identity. The three ODBC connection strings (BRIDGE_CONTROL_ODBC, BRIDGE_SYNAPSE_AUDIT_ODBC, BRIDGE_CETAS_ODBC) are in the secret store. | README.md step 2; WHERE_TO_ENTER_VALUES.md | [5 empty] | Not started |  |  | Ready
2 | A. Platform setup | Azure SQL control database | 01_azure_sql_control.sql run (or 03_upgrade_to_v9_5.sql for v9 to v9.5.5). One bridge.source_fence seed row inserted. Orchestration identity granted its rights, including SELECT on bridge.fence_events. | sql/01, sql/03 | 1 |  |  |  |  | Not started |  |  | Waiting
3 | A. Platform setup | Synapse setup | Database master key created by an administrator. 02_synapse_setup.sql run with the real ADLS LOCATION. Database-scoped CETAS grants applied. Managed identity has write/list access to staging. | sql/02; DESIGN_v9.md section 4 | 1 |  |  |  |  | Not started |  |  | Waiting
4 | A. Platform setup | ADLS and Unity Catalog storage | Storage credential (Access Connector) and external location created. READ FILES granted to all four Job identities. Storage firewall and serverless network access configured. Leaf-path read validated as the loader identity. | WHERE_TO_ENTER_VALUES.md (external location) | 1 |  |  |  |  | Not started |  |  | Waiting
5 | A. Platform setup | Control host | Python 3.9+, ODBC Driver 18 and requirements.txt installed. Databricks unified authentication and DefaultAzureCredential working. Host can read/list staging and create job manifests under _manifests/. | README.md step 2; requirements.txt | 1 |  |  |  |  | Not started |  |  | Waiting
6 | B. Inventory and deployment | First-wave inventory | Mappings generated and exceptions reviewed. profile_thresholds added by hand, then profiled. REPLACE_TABLE / RELEASE_POINTER and groups chosen. Every <...> value filled. Versioned config.json saved on the control host. | generate_mappings.py, profile_inventory.py, source_metadata.py | 3 | 5 |  |  |  | Not started |  |  | Waiting
7 | B. Inventory and deployment | Render and apply setup SQL | render_setup.py run. azure_sql_seed.sql applied in Azure SQL; unity_catalog_setup.sql applied on a SQL warehouse. Governed policies applied to physical tables. | render_setup.py; README.md step 5 | 2 | 6 |  |  |  | Not started |  |  | Waiting
8 | B. Inventory and deployment | Databricks Jobs and Copy pipeline | Four serverless Jobs created: auto-optimization off, timeout <= 7,200 s, concurrent runs >= worker limits, manifest parameters with empty defaults. Job IDs in config. Copy pipeline deployed only if COPY_ACTIVITY is used. | WHERE_TO_ENTER_VALUES.md (Jobs); deploy_synapse_pipeline.py | 1 | 4 | 6 |  |  | Not started |  |  | Waiting
9 | C. Controls left to you | Upstream scheduler integration | Existing Synapse transformations wrapped with write-start, upstream_audit.py, write-close and bridge-hold. Every source writer identity listed. Permissions that bypass the fence removed. | fence.py; upstream_audit.py; IMPLEMENTATION_STATUS.md (fence) | 2 | 3 |  |  |  | Not started |  |  | Waiting
10 | C. Controls left to you | Independent source detectors | Monitoring produces fence_evidence.json with five checks, each with an evidence URI: all_source_requests_terminal, no_source_retry_needed, audit_healthy, no_fence_violation, smoke_check_passed. | fence.py bridge-release; IMPLEMENTATION_STATUS.md | 9 |  |  |  |  | Not started |  |  | Waiting
11 | C. Controls left to you | Policy and consumer readiness tests | Tests run under the correct restricted identities and produce publication_evidence.json from real results (never hand-entered true values). | publish_run.py; README.md (evidence file formats) | 7 |  |  |  |  | Not started |  |  | Waiting
12 | C. Controls left to you | Gaps needed only for your data | Decision recorded for each: empty-result publication, TIME / time-zone / ancient-date / nested / LOB handling, staging quarantine and legal holds, rollback runbook (rollback is manual). | IMPLEMENTATION_STATUS.md (not implemented rows) | 6 |  |  |  |  | Not started |  |  | Waiting
13 | D. Platform testing | End-to-end acceptance run | One small wave runs nightly sequence end to end. Tested: values containing ¦, ", CR and LF; Copy Activity null and type behaviour; midnight-UTC date narrowing; managed-identity credential. | README.md 'Also noted'; IMPLEMENTATION_STATUS.md v9.5.7 | 8 | 9 | 10 | 11 |  | Not started |  |  | Waiting
14 | D. Platform testing | Concurrency and recovery on the platform | Proven: Delta row-level concurrency and conflict exception names in publish.py; Azure SQL row locks; Synapse etag / async behaviour; MANAGE + CREATE TABLE enough for CREATE OR REPLACE TABLE; timeout and takeover; recovery drills R1 to R4. | IMPLEMENTATION_STATUS.md v9.5.2 to v9.5.8; README.md | 13 |  |  |  |  | Not started |  |  | Waiting
15 | D. Platform testing | Performance and SLO benchmarking | Representative full-volume objects and the full estate benchmarked. Worker and class limits and Job concurrent-run limits tuned. | IMPLEMENTATION_STATUS.md (Throughput/SLO) | 13 |  |  |  |  | Not started |  |  | Waiting
16 | E. Operations handover | Scheduling, monitoring and runbooks | Nightly sequence and weekly retention scheduled. Alerting in place. Runbooks written for R1 to R4 and rollback. | SCRIPT_GUIDE.md Phase C and D | 14 | 15 |  |  |  | Not started |  |  | Waiting
17 | E. Operations handover | Fix package documentation | profile_thresholds statement in WHERE_TO_ENTER_VALUES.md corrected, or the block added to config.example.json. | WHERE_TO_ENTER_VALUES.md; config.example.json | [5 empty] | Not started |  |  | Ready

## Summary
Progress summary
Group | Tasks | Not started | In progress | Blocked | Done | % done | Ready to start
A. Platform setup | 5 | 5 | 0 | 0 | 0 | 0% | 1
B. Inventory and deployment | 3 | 3 | 0 | 0 | 0 | 0% | 0
C. Controls left to you | 4 | 4 | 0 | 0 | 0 | 0% | 0
D. Platform testing | 3 | 3 | 0 | 0 | 0 | 0% | 0
E. Operations handover | 2 | 2 | 0 | 0 | 0 | 0% | 1
Total | 17 | 17 | 0 | 0 | 0 | 0% | 2
Critical path
1 → 2 / 3 / 4 → 6 → 7 → 8 → 9 → 13 → 14 → 16
Start 10 and 11 early: they depend on your own monitoring and governance tools.

## Legend
How to use this tracker
Yellow cells | The only cells to edit: Owner, Status, Start date, Target date, Notes / risks (Tracker tab).
Status | Pick from the list: Not started, In progress, Blocked, Done.
Dep 1 to Dep 4 | Task IDs that must be Done first. You can change them; Readiness follows.
Readiness | Formula. Ready = every dependency is Done. Waiting = at least one is not. Done = this task is Done.
Target date | Shown in red when it has passed and the task is not Done.
Summary tab | Counts and % done per group update from the Status column.
Source | Tasks come from the package's IMPLEMENTATION_STATUS.md, README.md and WHERE_TO_ENTER_VALUES.md (v9.5.8).
Example row (format only) | Owner: Priya S. ¦ Status: In progress ¦ Start date: 28-Sep-2026 ¦ Target date: 02-Oct-2026 ¦ Notes: Waiting on firewall change CHG-1234